## ProjectTeam
Name | GitHub Alias
Amanda | amand4msk
Jocelyn | jocelynthode
Simon | simonbru
Michael | jungomi
Fisnik | mengja
Andrea | liechtia

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Manage Account | As a Guest, I need to create an account, to be part of community, be able to view and change the account informations | high | 30 |  | 4 | In Progress
2 | User roles | As a User, I need to have two roles, as a coach and as a trainee, to be able to offer training session and also to take training session | high | 30
3 | Courses subscription | As a User, I need to be able to subscribe and unsubscribe to courses, to see and to participate in his/her activity and see the different training sessions | high | 30
4 | Manage Courses | As a User, I need to able to create courses and training session for my subscribers, showing the place in the map, time and date when it will take place, and registration expiry date. I should also be able to cancel them (delete). | medium | 40
5 | Communicate with trainees | As a Coach, I need to be able to communicate with my subscribers (multicasting), to share something with them or remind them of a training | low | 30
6 | Rating coaches | As a Subscriber, I need to be able to rate my coaches after training session has taken place, giving a feedback that helps other users | low | 16
7 | View all Courses | As a User, I need to be able to view all courses, all courses by my coaches and all courses i am subscribed to | medium | 12 |  |  | In Progress
8 | Follow coaches | As a User, I am able to follow coaches that I like so I can easily be informed when these coaches offer new courses | low | 20
9 | Search Engine | As a User, I need to search for courses to find easily find available courses that interest me. | medium | 30
10 | Share courses on Facebook | As a Coach, I need to be able to share my course on Facebook | low | 16
11 | Calendar | As a Coach and as a User, I need to be able to export the training session date to the "Google Calendar" I can also see a list of the next training sessions | low | 25
12 | Exposing future training sessions and Coaches | As a Guest, I want to see all future; training sessions, events, coachs etc. but I can not subscribe to a particular coach or training session without registration. | medium | 35
|  |  | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
314

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180